### Tournament Planning Checklist

#### Initial Planning (6-12 Months Before)

- Define the tournament’s scope

- Determine the sports to be included.

- Decide on the tournament format (single elimination, double elimination, round-robin, etc.).

- Establish age and grade divisions.

- Select dates and venues

- Choose potential dates and confirm with school administration.

- Reserve venues and ensure they have the necessary facilities (fields, courts, locker rooms, restrooms, etc.).

- Form a planning committee

- Assign roles: Tournament Director, Registration Coordinator, Marketing Coordinator, Volunteer Coordinator, etc.

- Schedule regular planning meetings.

- Create a budget

- Estimate costs for venue rental, equipment, officials, marketing, awards and other expenses.

- Identify potential revenue sources (registration fees, sponsorships, concessions).

#### Intermediate Planning (3-6 Months Before)

- Secure sponsors and partners

- Create sponsorship packages.

- Reach out to local businesses, community organizations and potential sponsors.

- Develop marketing and promotion plan

- Design promotional materials (flyers, posters, social media graphics).

- Plan social media campaigns and press releases.

- Open registration

- Set up online and paper registration forms.

- Announce registration opening to schools, teams and the community.

- Organize volunteers

- Recruit volunteers for various roles (registration, setup, scorekeeping, concessions, etc.).

- Schedule volunteer training sessions.

#### Detailed Planning (1-3 Months Before)

- Finalize schedules and brackets

- Create match schedules and tournament brackets.

- Ensure enough time between matches for rest and venue turnover.

- Order equipment and supplies

- Order sports equipment, uniforms, first aid kits and other necessary supplies.

- Arrange for delivery and storage.

- Arrange for officials and referees

- Hire and schedule officials for each sport.

- Provide rulebooks and training as needed.

- Coordinate with venue management

- Confirm venue arrangements and facilities.

- Plan for venue setup and cleanup.

#### Pre-Tournament Preparation (1-4 Weeks Before)

- Confirm registrations and payments

- Verify all team and individual registrations.

- Ensure all registration fees have been collected.

- Distribute tournament information

- Send schedules, brackets and venue maps to participants.

- Provide information on rules, code of conduct and emergency procedures.

- Plan for medical and emergency services

- Arrange for on-site medical personnel.

- Prepare emergency contact lists and procedures.

- Organize merchandise and awards

- Order and organize tournament merchandise (t-shirts, hats, etc.).

- Ensure medals, trophies and certificates are ready.

#### Tournament Day(s)

- Setup and opening

- Set up registration tables, signage and equipment.

- Conduct a briefing with volunteers and officials.

- Welcome participants and conduct opening ceremonies.

- Manage matches and activities

- Ensure matches start and end on time.

- Handle any disputes or issues that arise.

- Provide regular updates on scores and standings.

- Monitor safety and compliance

- Ensure all participants follow rules and conduct codes.

- Address any injuries or emergencies promptly.

#### Post-Tournament

- Closing and cleanup

- Conduct closing ceremonies and award presentations.

- Clean up venues and return any rented equipment.

- Collect feedback

- Distribute and collect feedback forms from participants, parents and volunteers.

- Review feedback for future improvements.

- Financial reconciliation

- Finalize all financial transactions.

- Prepare a financial report detailing income and expenses.

- Post-event report

- Compile a comprehensive report summarizing the tournament.

- Include successes, challenges and recommendations for future events.

- Send thank you notes

- Thank sponsors, volunteers, officials and participants.

- Recognize exceptional contributions and support.